## Dynamic Gantt Chart
Dynamic Excel Gantt Chart (Reloaded) |  | [Project Title]
Article: | Dynamic Gantt Chart Template | Start Date: |  |  | 2013-01-01 |  | Project Manager: | [Name]
All Templates: | Excel Templates by Robert McQuaig | End Date: |  |  | 2013-12-31 |  | Project Sponsor: | [Name]
© 2012-2013 Robert McQuaig Blog
|  | WBS | Status |  |  | Task Name | Start Date | End Date | Dur.
|  | 1 | 1 | Complete |  | Scope Review | 2013-01-02 | 2013-03-15 | 72
|  | 1.1 | 1 | Complete |  | Budget Planning | 2013-02-01 | 2013-04-01 | 59
|  | 1.2 | 1 | Complete |  | Charter Signoff | 2013-03-01 | 2013-04-17 | 47
|  | 1.2.1 | 1 | Complete |  | Project Acceptance | 2013-04-17 | 2013-05-01 | 14
|  | 1.2.2 | 1 | Complete |  | Project Initiation | 2013-05-01 | 2013-05-10 | 9
|  | 1.3 | 50 | At Risk |  | Execute Contracts | 2013-05-01 | 2013-05-30 | 29
|  | 1.4 | 50 | At Risk |  | Procurements | 2013-05-01 | 2013-05-30 | 29
|  | 1.5 | 25 | Late |  | Development Environment | 2013-05-20 | 2013-06-25 | 36
|  | 2 | 75 | On Schedule |  | Application Build | 2013-06-25 | 2013-10-01 | 98
|  | 2.1 | 75 | On Schedule |  | Testing / Acceptance | 2013-09-01 | 2013-10-01 | 30
|  | 2.2 | 75 | On Schedule |  | Production Environment | 2013-09-10 | 2013-10-31 | 51
|  | 2.3 | 75 | On Schedule |  | Training | 2013-09-20 | 2013-10-31 | 41
|  | 2.4 | 75 | On Schedule |  | Documentation Updates | 2013-10-15 | 2013-11-01 | 17
|  | 2.5 | 75 | On Schedule |  | Stage Roll | 2013-11-01 | 2013-11-10 | 9
|  | 3 | 75 | On Schedule |  | Go / NoGo | 2013-11-09 | 2013-11-20 | 11
|  | 3.1 | 75 | On Schedule |  | Production Roll | 2013-11-20 | 2013-12-15 | 25
|  | 3.2 | 75 | On Schedule |  | Communication | 2013-12-10 | 2013-12-20 | 10
|  | 3.3 | 75 | On Schedule |  | Project Closure | 2013-12-10 | 2013-12-31 | 21
0
0
General Notes:
1. Fill in the gantt chart by completing in the sections on rows 6 through 61.
2. Insert new rows by adding lines BEFORE the last row, ensuring that the chart is captured in the insert function. When the new lines are added (properly) the chart will update accordingly.
3. Stretch the size of the chart, to update the size/scale of the project. In addition, update the print preview to switch between gantt chart, task items, or both (default)
4. Update the colors simply by clicking on the chart bar and changing the color as you see fit.